## Overview
Activities | Detailed activity | Quality and progress indicators | Means of verification
Preparation
| OSAT development | Online tool created and final version approved by ECOO | Written confirmation from ECOO
| Pedagogical data collection at partner HEIs | All data collected at all 6 partner organisations | Data collection records completed
| Conversion of credits to ECTs | Course credits at all 6 partner organisations converted to ECTs | Written confirmation from each organisation
| Preliminary gap analysis | Gap analysis report provided to each partner organisation | Gap analysis document from ECOO
Follow-up pedagogical data collection
| Follow-up gap analysis | Gap analysis report provided to each partner organisation | Gap analysis document from ECOO
Development
| Mentoring | Notes from meetings
| PTP and EBP development workshop | Workshop format and outputs | Minutes of London June 2017 meeting
| Update of pedagogical transformation plan |  | Most available on the portal, but UOH not visible - UOH advised to check and upload.
| Development of Syllabi and Teaching and assessment Materials for PTP |  | Informatiion on Portal - some still to be uploaded. Teaching manual being developed and will be uploaded.
| Literature search and appraisal of research evidence on EBP education in health care. | Completed prior to EBP/PTP planning meeting in London, June 2017 | Minutes of June meeting, showing presentation on results of this process
| Find and Appraise Existing Resources for EBP | Programme evaluation completed by each institution
| PTP and EBP workshops | Quality evaluation questionnaire | Workshop evaluations uploaded to portal.
| Develop manuals for the EBP teaching methods | First draft circulated October 2017 | Draft and later final product
| Portal development | Minutes of meeting in Barcelona November 2016 | Portal itself
| Portal technical support, maintenance and updates | Initially was being developed by Sapir but due to progress issues this has been taken up by CU. | Documented in mid-term report and in minutes of QA meetings.
| PLN development | Was intended to be ready for piloting but was delayed beyond this. PLN was reduced at this point to log book. Responsibility for log book taken over by UOH Oct 2018.
| PLN implementation | Delayed. Discussed at CM3 and UOH have a clear idea how to move forward.
| TTT workshop planning | Logistical challenge to plan these but challenges were overcome. | On portal.
TTT workshop implementation
| Pilot module implementation | Pilots took place on time but without PLN. The team feels that quality is not compromised. | Evaluation will be uploaded on the portal.
| Continuing education workshops in partner countries | As at CM3: some pilot workshops have taken place, but are continuing.
Quality control
| Milestone/Output maps developed for each project component | Details on mapping document | Mapping document (current spreadsheet)
Implementation of milestone/output maps
| Annual project evaluation | Taking place at each CM.
Dissemination
| Dissemination campaign at each HEI |  | Dissemination details on portal
| Dissemination via participation in National and international conferences and meetings | Considerable dissemination has occurred and is continuing.
| Dissemination to and via optometry associations | Occurring on an ongoing basis. | Documents and web sites
| Sustainability plan |  | Meeting minutes.
Management
Partners agreements and project hand book
Project Governors' Board
Control and Monitoring
Communication
| Consortium meeting 1 | Meeting minutes and evaluation | Meeting minutes and evaluation
| Consortium meeting 2 | Meeting minutes and evaluation | Meeting minutes and evaluation
| Consortium meeting 3 | Meeting minutes and evaluation | Meeting minutes and evaluation

## Preparation
Activity | Comments on progress and quality | Comments on any remedial action
CM1 finalises work plans
Creation of OSAT | Late development
Pedagogical data collection at partner HEIs
Conversion of credits to ECTs
Preliminary gap analysis
Follow-up pedagogical data collection
Follow-up gap analysis

## Development
Activity | Comments on progress and quality | Comments on any remedial action
Mentor Assignment
PTP development workshop
Update of pedagogical transformation plan
Write a PTP recommendation guide.
Consortium meeting 2 – Israel
Literature review and mentorship from programme country HEI sharing best practices from programme country HEI
Development of Syllabi and Teaching Materials PTP and assessment measures
Literature search and appraisal of research evidence on EBP education in health care.
Find and Appraise Existing Resources
Workshop Planning
Workshops to develop educational resources for EBP
Develop manuals for the EBP teaching methods
Portal needs analysis, and functional requirements design
Portal infrastructure development
Portal development
Testing procedures and documentation
Portal training kit and training sessions
Portal technical support, maintenance and updates
PLN needs analysis, and functional requirements design
PLN infrastructure development
PLN development cycle 1 – patient logging

## Quality control
Quality Committee | 2016 | Revised committee date:
Institution | Name | Name
CUL
HAC
UOH
UPC
CU
MU
USN
BIU
HU
SAP
ASCO
Activity | Comments on progress and quality | Comments on any remedial action
Milestone/Output maps developed for each project component
Implementation of milestone/output maps
Annual project evaluation

## Dissemination
Activity | Comments on progress and quality | Comments on any remedial action
Dissemination campaign at each HEI
Dissemination via participation in National and international scientific meetings
Dissemination via World Council of Optometry
Dissemination to and via optometry associations

## Management
Activity | Comments on progress and quality | Comments on any remedial action
Partners agreements and project hand book
Project Governors' Board
Control and Monitoring
Communication